## Sheet1
Sr.Number | ToDo: | Status | Assigned | Comment
1 | Inline Css | Onhold | Sharmila
2 | login page text box width | OnHold | Sharmila
3 | Multiple layout pages | OnHold | Sharmila
4 | prescription and navigation not working well | Done | Taniya
5 | User need to click on Print button at many times to print prescription E.g. Click on button "PrintPrescription" then click on Print then click on print. We should allow user to click only once to print prescription | Done | Taniya
6 | Grid or popup should display on clinical examination and Investigation .e.g . If patient came 4 times as OPD so user should able to see patient BP values according to OPD Date | Done | Taniya
7 | user cannot scroll year in dob control | Done | Taniya
8 | add new patient if patient is female spouse should get updated as male | Done | Taniya
9 | add patient form needs to design properly | Working | Sharmila
10 | upload file button look needs to change | Working | Sharmila
11 | automatic logoff should get removed and add button for logoff | Done | Taniya | Once session timeout it gets log off. I update the session timeout after 30min from ideal. If its still not working please let me know.
12 | Add one more column in prescription intake adv (medicine should take after food / before food / not appplicable/ in morning immidietly after get up/ In night before bed) | Done | Taniya
13 | Please change the backgroud color. | Working | Sharmila
14 | Default save message should get removed. | Done | Taniya
15 | Submit button and Button style should same | Done | Taniya